## Sheet1
Project Phase (Main Task -> Sub-Task) |  |  |  |  | Duration | Start | Finish | February | [7 empty] | March |  |  |  |  | April |  |  |  |  | May | [6 empty] | June
M | Alloc. |  |  |  |  | 2021-02-01 | 2021-06-10 | 2021-02-01 |  | 2021-02-08 |  |  |  | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 |  | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 |  | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-05-24 | 2021-05-31 |  | 2021-06-07
Prototyping |  |  |  |  | 35 | 2021-02-01 | 2021-03-19 | Prototyping Phase
| Test Video Output IP |  |  |  | 20 | 2021-02-01 | 2021-02-26 | Test Video Output IP
| ♥♣▲ | Research PMOD->DVI IP |  |  | 10 | 2021-02-01 | 2021-02-12 |  | ♥ |  | ♣ |  | ▲
| ♦♠ | Obtain PMOD->DVI Connector |  |  | 10 | 2021-02-01 | 2021-02-12 |  | ♦ |  |  | ♠
|  | Create data transfer test |  |  | 10 | 2021-02-15 | 2021-02-26
★ |  | Verify data transfer functionality |  |  | 5 | 2021-02-22 | 2021-02-26
| Develop SoC's Graphic Block Prototype |  |  |  | 30 | 2021-02-01 | 2021-03-12 | Develop SoC's Graphic Block Prototype
|  | Research HW graphics buffer |  |  | 10 | 2021-02-01 | 2021-02-12
|  | Create Peripherals<->Graphics switch |  |  | 5 | 2021-02-15 | 2021-02-19
|  | Create HW block switch test |  |  | 2 | 2021-02-16 | 2021-02-17
|  | Verify HW block switching capability |  |  | 2 | 2021-02-18 | 2021-02-19
|  | Create HW graphic buffer |  |  | 10 | 2021-02-15 | 2021-02-26
|  | Create buffer data->DVI transfer test |  |  | 5 | 2021-02-22 | 2021-02-26
★ |  | Verify buffer data transmission |  |  | 2 | 2021-02-25 | 2021-02-26
|  | Add extra functionality to block |  |  | 10 | 2021-03-01 | 2021-03-12
|  | Create full Graphic Block test |  |  | 2 | 2021-03-09 | 2021-03-10
|  | Very full Graphic Block functionality |  |  | 2 | 2021-03-11 | 2021-03-12
| Develop Debian/Linux Driver Prototype |  |  |  | 35 | 2021-02-01 | 2021-03-19 | Develop Debian/Linux Driver Prototype
|  | Research Linux device drivers |  |  | 10 | 2021-02-01 | 2021-02-12
|  | Research driver framebuffers |  |  | 10 | 2021-02-15 | 2021-02-26
|  | Create basic Debian device driver |  |  | 5 | 2021-02-15 | 2021-02-19
|  | Add framebuffer & basic functionality |  |  | 10 | 2021-02-22 | 2021-03-05
|  | Create basic driver test |  |  | 2 | 2021-03-02 | 2021-03-03
★ |  | Verify current driver functionality |  |  | 2 | 2021-03-04 | 2021-03-05
|  | Add advanced functionality |  |  | 10 | 2021-03-08 | 2021-03-19
|  | Create advanced driver test |  |  | 5 | 2021-03-15 | 2021-03-19
|  | Verify advanced driver functionality |  |  | 2 | 2021-03-18 | 2021-03-19
Project Overlook 1 |  |  |  |  | 15 | 2021-03-15 | 2021-04-02 | [10 empty] | Project Overlook 1
| Winter Term Finals (Dead Week) |  |  |  | 5 | 2021-03-15 | 2021-03-19
★ | Team Project Review |  |  |  | 3 | 2021-03-22 | 2021-03-24
| Develop Integration & Test Plans |  |  |  | 10 | 2021-03-22 | 2021-04-02
Integration |  |  |  |  | 20 | 2021-04-05 | 2021-04-30 | [14 empty] | Integration
| Establish Driver and HW connections |  |  |  | 10 | 2021-04-05 | 2021-04-16 | [14 empty] | Con. Driver & HW
|  | Connect driver to Graphic Block controls |  |  | 5 | 2021-04-05 | 2021-04-09
|  | Create Graphic Block control test |  |  | 1 | 2021-04-08 | 2021-04-08
|  | Verify basic driver/HW interoperability |  |  | 1 | 2021-04-09 | 2021-04-09
|  | Connect driver & HW framebuffers |  |  | 5 | 2021-04-12 | 2021-04-16
|  | Create framebuffer transfer test |  |  | 2 | 2021-04-14 | 2021-04-15
★ |  | Verify full driver/HW interoperability |  |  | 1 | 2021-04-16 | 2021-04-16
| Develop User Space API |  |  |  | 20 | 2021-04-05 | 2021-04-30 | [14 empty] | Develop User Space API
|  | Plan out API |  |  | 10 | 2021-04-05 | 2021-04-16
|  | Code API with basic functionality |  |  | 10 | 2021-04-19 | 2021-04-30
|  | Create functionality tests |  |  | 5 | 2021-04-26 | 2021-04-30
★ |  | Verify API functionality |  |  | 2 | 2021-04-29 | 2021-04-30
Project Overlook 2 |  |  |  |  | 5 | 2021-04-26 | 2021-05-05 | [17 empty] | Project Overlook 2
| Spring Term Midterms (Dead Week) |  |  |  | 5 | 2021-04-26 | 2021-04-30
★ | Team Project Review |  |  |  | 3 | 2021-05-03 | 2021-05-05
Testing |  |  |  |  | 20 | 2021-05-03 | 2021-05-28 | [19 empty] | Testing
| API Finalization |  |  |  | 10 | 2021-05-03 | 2021-05-14 | [19 empty] | API Finalization
|  | Develop very basic programs using API |  |  | 5 | 2021-05-03 | 2021-05-07
|  | Update API based on dev experience |  |  | 5 | 2021-05-10 | 2021-05-14
|  | Create API functionality test |  |  | 2 | 2021-05-13 | 2021-05-14
★ |  | Verify full API functionality |  |  | 1 | 2021-05-14 | 2021-05-14
| Develop User Space Program |  |  |  | 10 | 2021-05-17 | 2021-05-28 | [21 empty] | Dev. User Program
|  | Create demonstration program |  |  | 10 | 2021-05-17 | 2021-05-28
|  | Create test for program |  |  | 2 | 2021-05-25 | 2021-05-26
★ |  | Verify program functionality |  |  | 2 | 2021-05-27 | 2021-05-28
Documentation and Final Report |  |  |  |  | 15 | 2021-05-20 | 2021-06-09 | [22 empty] | Documentation and Final Report
| Clean Up Documentation |  |  |  | 7 | 2021-05-20 | 2021-05-28
| Prepare Final Presentation |  |  |  | 5 | 2021-05-31 | 2021-06-04
★ | Write Final Report |  |  |  | 8 | 2021-05-31 | 2021-06-09
Key -> |  |  | Software Team | Hardware Team |  | Entire Team |  | Milestone = ★ ¦ ★ | [5 empty] | Ahmad ♥ | Hector ♦ | Jack ♣ | Ross ♠ | Ryan ▲